IMPLEMENTATION PLAN

THE WITNESS

12-Milestone Delivery Roadmap

Companion to the Solution Architecture Design Document

Prepared for: Technical and Executive Stakeholders

Prepared by: Solution Architecture

Version 1.0 — July 2026

Status: Draft for Review

# Table of Contents

# How to Read This Plan

This document expands the 12-milestone roadmap from the Solution Architecture Design Document into an execution-ready implementation plan. Each milestone is scoped to be independently developed, tested, and deployed — building on the milestones before it but shippable on its own, so editorial and engineering stakeholders see working functionality incrementally rather than waiting for a single big-bang release.

Every milestone follows the same structure: objective, scope, features, user stories, database changes, API endpoints, UI screens, components, state management approach, Supabase-specific changes, AI integrations, acceptance criteria, testing strategy, risks and dependencies, and an estimated complexity. No implementation code is included in this document by design — it is a planning and sequencing artifact; code generation follows milestone-by-milestone once each scope is approved, per the development process defined in the original product specification.

## Roadmap Summary

| # | Milestone | Complexity | Duration | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Project Setup and Architecture | S | 1–2 weeks | None (first milestone) |
| 2 | Authentication and User Roles | M | 2–3 weeks | Milestone 1 |
| 3 | Publication Management | M | 2 weeks | Milestone 2 |
| 4 | Issue Builder | L | 3–4 weeks | Milestone 3 |
| 5 | AI Workspace | L | 3–4 weeks | Milestones 3, 4 |
| 6 | Wisdom Engine | M | 2–3 weeks | Milestones 2, 4 |
| 7 | Knowledge Graph | M | 2–3 weeks | Milestones 4, 6 |
| 8 | Search | M | 2–3 weeks | Milestones 5, 7 |
| 9 | Analytics | M | 2 weeks | Milestones 3, 4, 5, 6, 7 |
| 10 | Publishing Pipeline | L | 3 weeks | Milestones 3, 4, 9 |
| 11 | Performance Optimization | M | 2 weeks | Milestones 1–10 |
| 12 | Production Deployment | M | 2 weeks, plus remediation buffer | Milestones 1–11 |

Complexity legend: S = Small (1–2 weeks) · M = Medium (2–3 weeks) · L = Large (3–4 weeks) · XL = Extra Large (4+ weeks). Total estimated duration across all 12 milestones: approximately 28–33 development weeks for a small, focused team, excluding remediation buffers called out in Milestones 11–12.

## Milestone Dependency Sequence

Figure 1. Milestone dependency graph. Milestones 5, 6, and 7 can proceed in parallel once Milestone 4 is complete, provided team capacity allows; Milestone 8 depends on both 5 and 7.

## Cross-Cutting Practices Applied to Every Milestone

- Row Level Security is verified for every new or changed table as part of that milestone's own testing — RLS review is never deferred to a later “security milestone.”

- Every milestone that introduces a new table extends the shared conventions established in Milestone 1 (UUID keys, timestamps, audit-friendly change tracking).

- Acceptance criteria are written to be objectively verifiable, so each milestone has a clear, demonstrable Definition of Done rather than a subjective sign-off.

- A milestone is not considered complete until its own testing strategy has been executed — testing is integrated per milestone, not batched at the end of the project.

# Milestone 1: Project Setup and Architecture

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| S | 1–2 weeks | None (first milestone) |

## Objective

Establish the foundational technical scaffolding, environments, and delivery pipeline so every subsequent milestone builds on a stable, consistent base.

## Scope

In Scope

- Repository and monorepo layout (feature-based folder structure)

- Next.js 15 App Router scaffold, TypeScript strict mode, ESLint/Prettier

- Tailwind CSS and shadcn/ui installation and design-token setup (light/dark theme)

- Supabase project provisioning for development, staging, and production

- Vercel project setup and environment/secret configuration

- CI/CD pipeline: lint, typecheck, unit test, preview deployment on PR

- Base layout shell, error boundary, logging, and notification/toast provider

Out of Scope

- Any domain-specific tables or business logic (begins Milestone 2)

- AI provider integration (Milestone 5)

## Features

- Application shell and theme provider (light/dark mode)

- Environment/config loader with per-environment secrets

- CI pipeline enforcing lint/typecheck/test on every pull request

- Health-check endpoint for uptime monitoring

## User Stories

- As a Developer, I want a consistent, reproducible local development environment, so that I can start contributing without manual environment debugging.

- As a Developer, I want CI to block merges on failing lint, typecheck, or tests, so that the main branch always stays in a shippable state.

- As an Engineering Lead, I want an automatic preview deployment for every pull request, so that stakeholders can review UI changes before merge.

## Database Changes

- No domain tables yet. Enable required Postgres extensions: uuid-ossp / pgcrypto, pgvector (reserved for Milestone 8).

- Establish shared conventions migration: updated_at trigger function, standard UUID default, naming conventions used by every later migration.

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| GET | /api/health | Liveness/readiness check for uptime monitoring. |

## UI Screens

- Application shell (header/nav/footer placeholder)

- Internal style guide / component gallery (optional, aids design QA)

## Components

- AppShell

- ThemeProvider

- ErrorBoundary

- ToastProvider

- Base Button/Input/Card (shadcn baseline)

## State Management

Server Components and server-side data fetching as the default; minimal client state (theme, toasts) via React Context. No global data-fetching library is introduced yet — deferred until a milestone has real server state to manage (Milestone 3).

## Supabase Changes

- Create dev/staging/production Supabase projects

- Enable required extensions

- Configure base Auth settings (deferred activation to Milestone 2)

- Create a placeholder Storage bucket for media

## AI Integrations

- None. Reserve OPENAI_API_KEY and ANTHROPIC_API_KEY environment variable slots per environment for Milestone 5.

## Acceptance Criteria

- Application builds and runs locally and on a Vercel preview deployment

- CI pipeline runs and enforces lint, typecheck, and test on every PR

- Dev, staging, and production Supabase projects are provisioned and reachable

- Theme toggle switches light/dark mode correctly

## Testing Strategy

- Unit test harness configured (Vitest) with one passing example test in CI

- Smoke test against the health-check endpoint

- No domain/business-logic testing yet

## Risks and Dependencies

- No upstream dependency — this milestone blocks all others

- Tooling choices made here (testing framework, state approach) constrain later milestones; keep choices lightweight and swappable rather than heavyweight and rigid

# Milestone 2: Authentication and User Roles

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2–3 weeks | Milestone 1 |

## Objective

Implement identity, Role-Based Access Control, and the initial Row Level Security foundation that every subsequent feature depends on for authorization.

## Scope

In Scope

- Supabase Auth integration (email/password; OAuth optional)

- profiles table extending auth.users with role

- Organizations and organization membership

- Publication membership model (who belongs to which publication, at what role)

- Session handling via Next.js middleware

- Foundational RLS policies and an initial audit log

Out of Scope

- Publication content itself (Milestone 3)

- Fine-grained per-block permissions (introduced conceptually in Milestone 4)

## Features

- Sign up / sign in / sign out

- Password reset

- Profile management

- Role assignment (admin UI)

- Organization creation and member invitation

- Protected-route middleware

## User Stories

- As a new user, I want to sign up with my email, so that I can access the platform.

- As a Super Admin, I want to assign roles to editorial staff, so that access is scoped correctly to each person's responsibilities.

- As an Editor, I want to log in and see only the publications I'm a member of, so that I don't have to navigate irrelevant content.

- As an Enterprise Organization admin, I want to invite subscriber seats under my organization, so that my team can access the platform under one account.

## Database Changes

- profiles (id fk auth.users, full_name, avatar_url, role, created_at)

- organizations (id, name, type: enterprise/university, created_by)

- organization_members (organization_id, user_id, role)

- publication_members (publication_id, user_id, role) — created here, populated from Milestone 3 onward

- invitations (email, organization_id or publication_id, role, token, status, expires_at)

- audit_logs (actor_id, action, entity_type, entity_id, before, after, occurred_at) — initial version

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| POST | /api/auth/callback | Supabase Auth callback handler. |
| GET/PATCH | /api/profile | Read/update the current user's profile. |
| POST | /api/organizations | Create an organization. |
| POST | /api/organizations/:id/invite | Invite a member to an organization. |
| POST | /api/publications/:id/members | Add or update a publication member's role. |
| GET | /api/users | Admin: list and search users. |

## UI Screens

- Sign up

- Sign in

- Forgot / reset password

- Profile settings

- Admin: Users & Roles

- Organization creation and management

- Invitation acceptance flow

## Components

- AuthForm

- RoleBadge

- MembersTable

- InviteModal

- ProtectedRoute wrapper

- RoleGuard

## State Management

Session/user state provided via Supabase Auth server-side session, exposed to client components through a lightweight auth context. A centralized usePermissions hook wraps role/membership checks so authorization logic is not duplicated per screen.

## Supabase Changes

- Enable Auth providers; configure confirmation and password-reset email templates

- RLS policies on profiles, organizations, organization_members, publication_members (self can read/update own row; admins can manage within their scope)

- Audit trigger capturing role changes

## AI Integrations

- None.

## Acceptance Criteria

- Users can sign up, log in, log out, and reset their password

- Role assignment is restricted to Super Admin and Editor-in-Chief

- A dedicated RLS test suite confirms a user cannot read another organization's members

- Unauthenticated requests to protected routes redirect to sign-in

## Testing Strategy

- Unit tests for the permission hook covering every role

- Integration tests against a Supabase test project confirming RLS denies cross-organization reads

- End-to-end (Playwright) coverage of sign-up, sign-in, and password-reset flows

## Risks and Dependencies

- Depends on Milestone 1 scaffold being complete

- RLS policy gaps are the platform's highest-severity risk category — mitigated by a dedicated, continuously extended RLS test suite carried forward into every later milestone

- OAuth provider setup may be blocked on third-party app review timelines; email/password can ship first if needed

# Milestone 3: Publication Management

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2 weeks | Milestone 2 |

## Objective

Enable creation and configuration of publications as the platform's primary tenant/partition entity, which every later content and analytics feature scopes against.

## Scope

In Scope

- Publication CRUD (create, edit, archive)

- Branding configuration (logo, colors, fonts)

- Editorial guidelines authoring

- Publishing cadence configuration

- Template assignment stubs for email/PDF/web (full rendering arrives in Milestone 10)

Out of Scope

- Actual issue content (Milestone 4)

- Live email/PDF rendering (Milestone 10)

## Features

- Create / edit / archive a publication

- Brand configuration with live preview

- Editorial guidelines rich-text editor

- Cadence (frequency) settings

- Template selection per output channel

## User Stories

- As an Editor-in-Chief, I want to create a new publication, so that we can launch a new editorial product without engineering involvement.

- As a Designer, I want to configure brand colors and fonts for a publication, so that issues render on-brand across channels.

- As an Editor, I want to set editorial guidelines for a publication, so that contributors follow consistent editorial standards.

## Database Changes

- publications (id, name, slug, description, theme JSONB, branding JSONB, editorial_guidelines text, cadence, status, created_by, timestamps)

- publication_templates (publication_id, channel: email/pdf/web, config JSONB)

- Extends publication_members from Milestone 2 with real data as publications are created

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| GET/POST | /api/publications | List / create publications. |
| GET/PATCH/DELETE | /api/publications/:id | Read, update, or archive a publication. |
| POST | /api/publications/:id/archive | Archive a publication (soft-delete). |
| GET/PATCH | /api/publications/:id/templates | Read/update channel template configuration. |

## UI Screens

- Publications list

- Create / edit publication wizard

- Publication Settings: Branding tab, Editorial Guidelines tab, Cadence tab, Templates tab

- Archive confirmation dialog

## Components

- PublicationCard

- PublicationForm

- BrandColorPicker

- TemplatePreview

- CadenceScheduler

## State Management

Introduce a PublicationContext provider that scopes the active publication across the editorial UI and drives publication_id filtering on subsequent data fetches. Form state via react-hook-form with schema validation.

## Supabase Changes

- RLS policies on publications and publication_templates scoped by publication_members role

- Storage bucket for branding assets (logos, brand imagery)

## AI Integrations

- None.

## Acceptance Criteria

- A Super Admin or Editor-in-Chief can create, edit, and archive a publication

- Branding changes are reflected in a live preview before saving

- RLS confirms only members of a publication can view or edit its settings

## Testing Strategy

- Unit tests on publication form validation

- Integration tests covering CRUD endpoints and their RLS enforcement

- Optional visual regression test on the branding preview

## Risks and Dependencies

- Depends on Milestone 2 roles and RLS foundation

- The theme/branding JSONB schema needs to anticipate Issue Builder rendering needs (Milestone 4); schema should be reviewed jointly with the Issue Builder design before being frozen

# Milestone 4: Issue Builder

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| L | 3–4 weeks | Milestone 3 |

## Objective

Deliver the block-based content editor that is the core editorial authoring surface, including draft/publish workflow and version history.

## Scope

In Scope

- issues / sections / blocks data model

- Drag-and-drop block editor UI

- Standard and editorial block type library

- Autosave and basic version history

- Draft → review → publish / schedule workflow

Out of Scope

- AI-generated block content (Milestone 5)

- Automatic wisdom-entry recommendation (Milestone 6 provides manual attach only)

- Actual email/PDF/public-web rendering of a published issue (Milestone 10)

## Features

- Create an issue within a publication

- Add, reorder, and delete content blocks

- Full block type library: Heading, Paragraph, Image, Quote, Table, Chart, Hero Story, Signal Card, Career Insight, Research Summary, Timeline, GitHub Repository, Book Recommendation, Company Profile, Technology Radar, Today's Wisdom (manual entry), Reflection, Action Checklist, Decision Framework

- Autosave

- Version history / revision snapshots

- Publish now or schedule for later

## User Stories

- As a Writer, I want to add and reorder content blocks, so that I can compose an issue in the order I intend readers to experience it.

- As an Editor, I want to preview an issue before publishing, so that I can catch formatting or content problems first.

- As an Editor-in-Chief, I want to schedule an issue for a future publish date, so that issues go out on our editorial cadence without manual intervention.

- As a Researcher, I want to insert a Research Summary block with structured fields, so that the summary is consistent and reusable, not free-form text.

## Database Changes

- issues (id, publication_id, title, status, scheduled_at, published_at, created_by, timestamps)

- sections (id, issue_id, order)

- blocks (id, section_id, type, order, payload JSONB, created_by, ai_generated boolean, timestamps)

- issue_revisions (issue_id, snapshot JSONB, created_by, created_at)

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| GET/POST | /api/publications/:id/issues | List / create issues for a publication. |
| GET/PATCH/DELETE | /api/issues/:id | Read, update, or delete an issue. |
| POST | /api/issues/:id/blocks | Add a block to an issue. |
| PATCH/DELETE | /api/blocks/:id | Update or remove a block. |
| POST | /api/issues/:id/reorder | Persist new block/section ordering. |
| POST | /api/issues/:id/publish | Publish an issue immediately. |
| POST | /api/issues/:id/schedule | Schedule an issue for future publish. |
| GET | /api/issues/:id/revisions | List revision snapshots for an issue. |

## UI Screens

- Issue pipeline (kanban by status: draft / in review / scheduled / published)

- Issue Builder canvas

- Block insertion menu

- Block property panels (per block type)

- Issue preview (web / email / PDF toggle, static preview only at this stage)

- Publish / schedule modal

- Revision history viewer

## Components

- BlockCanvas

- BlockRenderer (per type)

- BlockToolbar

- DragHandle

- BlockPropertyPanel

- IssueStatusBadge

- PublishScheduleModal

- PreviewFrame

## State Management

Dedicated client-side editor store (Zustand) holding the block tree for optimistic drag-and-drop reordering, synced to the server via debounced autosave. List/pipeline views use server-rendered data with lightweight client refetch on status change.

## Supabase Changes

- RLS on issues / sections / blocks scoped by publication_id and role (Writers edit their own drafts; Editors edit all drafts within their publication; unpublished content is invisible to Subscriber-tier roles)

- Realtime channel per issue reserved for collaborative presence (can be stubbed this milestone, wired up if time allows)

## AI Integrations

- None yet. AI-labeled blocks (Today's Wisdom, Decision Framework) are manually authored placeholders in this milestone; AI-assisted generation is introduced in Milestone 5 using this same block model.

## Acceptance Criteria

- An editor can build a complete multi-block issue end-to-end and publish it

- Autosave prevents data loss on accidental refresh or navigation

- RLS prevents a Writer-role account from publishing without Editor-level permission

- Revision history captures at least the last N snapshots and supports restore

## Testing Strategy

- Unit tests per block renderer

- Integration tests for block CRUD and reorder endpoints

- End-to-end test authoring a full issue and publishing it

- Accessibility check on drag-and-drop reordering, including a keyboard-operable alternative

## Risks and Dependencies

- Depends on Milestone 3 (publication context) and Milestone 2 (roles)

- JSONB block payload schema can drift across many block types — mitigate with per-type schema validation enforced at the API layer

- Keyboard-accessible drag-and-drop is nontrivial to implement well; budget explicit time rather than treating it as an afterthought

# Milestone 5: AI Workspace

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| L | 3–4 weeks | Milestones 3, 4 |

## Objective

Implement AI-assisted issue draft generation: provider-agnostic orchestration, per-block prompt composition, job tracking, and human-in-the-loop review.

## Scope

In Scope

- ai_jobs tracking table

- Provider abstraction covering OpenAI and Claude

- Block-type-specific prompt composition

- Generation triggered from the Issue Builder, with per-block regeneration

- Interim context retrieval against existing Knowledge Graph / library tables (full semantic retrieval lands in Milestone 8)

Out of Scope

- Automatic wisdom-entry recommendation (depends on Search/Knowledge Graph maturity, addressed as a fast-follow after Milestone 8)

- Any autonomous publish action — AI output is always a draft

## Features

- “Generate Issue” trigger and parameter form (publication, date range, audience, tone, depth, output format)

- Per-block generation and independent regeneration

- Job status tracking with live progress

- Admin-configurable provider/model selection

- Token usage and cost tracking per job

## User Stories

- As an Editor, I want to generate a draft issue from a date range and audience setting, so that I can start from a strong first draft instead of a blank page.

- As an Editor, I want to regenerate just the Hero Story block, so that I don't have to discard an otherwise-good draft over one weak section.

- As an Engineering Lead, I want to see token cost per generation, so that we can monitor AI spend against budget.

- As a Super Admin, I want to configure which AI provider and model is used by default, so that we can balance quality, latency, and cost as models evolve.

## Database Changes

- ai_jobs (id, publication_id, issue_id, block_id nullable, status, provider, model, params JSONB, prompt, result JSONB, token_usage, cost, error, created_by, timestamps)

- prompt_templates (id, block_type, template_text, variables JSONB)

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| POST | /api/issues/:id/ai/generate | Trigger full-issue AI draft generation. |
| GET | /api/ai-jobs/:id | Poll/read a single AI job's status and result. |
| POST | /api/blocks/:id/ai/regenerate | Regenerate a single block. |
| GET | /api/publications/:id/ai-jobs | List AI job history for a publication. |
| PATCH | /api/settings/ai-provider | Admin: update default provider/model configuration. |

## UI Screens

- Generate Issue modal (parameter form)

- AI job progress panel (per-block status within the Issue Builder)

- AI job history / log screen

- Provider and model admin settings screen

## Components

- GenerateIssueModal

- AIJobStatusBadge

- AIJobProgressList

- RegenerateButton (embedded in BlockToolbar)

- ProviderConfigForm

## State Management

AI job status is pushed to the client via Supabase Realtime subscriptions rather than polling; generation results merge into the Milestone 4 block store as draft blocks flagged ai_generated=true, pending editorial review through the existing Issue Builder state.

## Supabase Changes

- RLS on ai_jobs scoped by publication membership

- Realtime enabled on ai_jobs for live status updates

- Provider API keys stored via secure server-side secret management, never exposed to the client bundle

- Per-role rate-limit tracking to bound generation request volume

## AI Integrations

- Internal AIProvider interface (generateBlock, summarize) implemented for both OpenAI and Claude

- Per-block-type prompt templates

- Retry-with-backoff and timeout handling on provider calls

- Token usage capture from provider responses for cost tracking

## Acceptance Criteria

- An editor can generate a full draft issue that populates the Issue Builder as editable blocks

- Regenerating one block does not alter or discard any other block

- A failed generation surfaces a clear, specific error and never corrupts existing content

- Token usage and cost are recorded per job

- No AI-generated content reaches subscribers without an explicit human publish action (inherits the Milestone 4 publish workflow)

## Testing Strategy

- Unit tests on the provider abstraction using mocked API responses

- Integration tests covering the full ai_jobs lifecycle (pending → running → complete / error)

- Latency benchmarking against the target SLA (see design document Section 11)

- Manual editorial QA on prompt quality and tone per publication

## Risks and Dependencies

- Depends on Milestone 4 (block model) and Milestone 3 (publication context)

- AI provider latency or outages are a direct user-facing risk — mitigated with timeouts, retries, and a graceful partial-failure UI

- Context retrieval is limited until Search and Knowledge Graph (Milestones 7–8) exist; this is a documented interim limitation, with prompt-quality review scheduled again after those milestones land

# Milestone 6: Wisdom Engine

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2–3 weeks | Milestones 2, 4 |

## Objective

Implement the structured, multi-lens wisdom content system, its specialized source tables, and the editorial/subject-matter review workflow.

## Scope

In Scope

- wisdom_entries and specialized source tables (Subhāṣitams, Gītā verses, Advaita principles)

- Multi-lens authoring UI (technology, career, leadership, decision-making)

- Category taxonomy

- Manual attachment of a wisdom entry to an issue's Today's Wisdom / Reflection blocks

- Editorial and subject-matter review/sign-off workflow

Out of Scope

- Automatic, theme-based wisdom recommendation (depends on Search/Knowledge Graph, scoped as a fast-follow after Milestone 8)

## Features

- Wisdom entry CRUD across all required fields (source text, IAST transliteration, translation, context, commentary, four lenses, reflection questions, exercises, suggested actions, related topics, references)

- Category management

- Source-specific entry types

- Attach a wisdom entry to an issue block

- Review/approval workflow with a distinct reviewer role

## User Stories

- As a Researcher, I want to author a wisdom entry with all required lenses, so that editors have a complete, ready-to-use entry rather than a partial draft.

- As an Editor, I want to browse wisdom entries by category and attach one to today's issue, so that I can quickly find content that fits the issue's themes.

- As a subject-matter reviewer, I want to approve a wisdom entry before it can be published, so that translations and attributions are vetted before reaching readers.

## Database Changes

- wisdom_categories (id, name, description)

- wisdom_entries (id, category_id, title, source_type, source_text, iast, translation, context, commentary, tech_lens, career_lens, leadership_lens, decision_lens, keywords[], review_status, reviewed_by, references JSONB, timestamps)

- subhashitams / gita_verses / advaita_principles (each fk to wisdom_entries, with source-specific fields)

- wisdom_reflection_questions, wisdom_exercises (child tables of wisdom_entries)

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| GET/POST | /api/wisdom-entries | List / create wisdom entries. |
| GET/PATCH/DELETE | /api/wisdom-entries/:id | Read, update, or remove a wisdom entry. |
| POST | /api/wisdom-entries/:id/submit-review | Move an entry into the review queue. |
| POST | /api/wisdom-entries/:id/approve | Approve an entry (reviewer role only). |
| GET | /api/wisdom-categories | List categories. |
| POST | /api/blocks/:id/attach-wisdom | Attach an approved wisdom entry to a block. |

## UI Screens

- Wisdom Library (browse/filter by category and review status)

- Wisdom Entry Editor (multi-tab: Source, Lenses, Reflection & Exercises, References)

- Review Queue (for approvers)

- Wisdom Picker modal (used from the Issue Builder)

## Components

- WisdomEntryForm (multi-tab)

- LensEditor

- ReviewStatusBadge

- WisdomPickerModal

- WisdomCard

## State Management

Multi-tab form state via react-hook-form with per-tab validation; review-workflow status driven by server state with optimistic UI updates on approve/reject actions.

## Supabase Changes

- RLS on wisdom_entries by role: Researchers and Writers create drafts; only an approver role can set review_status = approved; only approved entries are attachable to a published issue

- Audit log entries on every review-status transition

## AI Integrations

- None in this milestone. AI-assisted wisdom recommendation is a documented fast-follow once Search and Knowledge Graph (Milestones 7–8) provide the semantic matching this would require.

## Acceptance Criteria

- A complete wisdom entry with all required lenses can be authored and routed through review to an approved state

- An approved entry can be attached to an issue's wisdom block

- An unapproved entry cannot be attached to a published issue

- Category filtering returns correct results

## Testing Strategy

- Unit tests on multi-lens form validation

- Integration tests on review-state transitions and their RLS enforcement

- A content QA pass with an actual subject-matter reviewer against a representative sample of entries

## Risks and Dependencies

- Depends on Milestone 2 (roles) and Milestone 4 (block attachment)

- The editorial/legal review process for source material is a process risk as much as a technical one (see design document Section 10); a named reviewer role and review SLA should be agreed before this milestone starts, not discovered during it

# Milestone 7: Knowledge Graph

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2–3 weeks | Milestones 4, 6 |

## Objective

Connect technologies, companies, research, and other reference entities to content and to each other, enabling both editorial linking and reader exploration.

## Scope

In Scope

- Reference library tables: technologies, companies, sources, books, papers, courses, videos, podcasts, github_repositories

- Typed many-to-many junction tables between entities and content

- Entity detail pages and a related-entity graph view

- Technology Radar block data source

Out of Scope

- Full-text/semantic search over these entities (Milestone 8)

- AI-assisted auto-tagging or entity extraction (documented as a plausible later enhancement, not in scope here)

## Features

- Entity CRUD across all reference library types

- Link entities to articles, blocks, and wisdom entries

- Entity detail pages showing related entities

- Technology Radar block backed by real technology records instead of free text

## User Stories

- As a Researcher, I want to tag an article with related technologies and companies, so that readers can explore further from a single article.

- As a Reader, I want to click a technology and see related companies, research, courses, and wisdom principles, so that I can go deeper on a topic without a separate search.

- As an Editor, I want the Technology Radar block to pull from a maintained technology list, so that radar entries stay consistent across issues instead of being retyped each time.

## Database Changes

- technologies, companies, sources, books, papers, courses, videos, podcasts, github_repositories (each with core metadata fields)

- Typed junction tables (e.g., article_technologies, article_companies, technology_companies) rather than one generic polymorphic link table, per design document Section 6.1

- entity_tags

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| GET/POST | /api/entities/:type | List / create entities of a given reference type. |
| GET/PATCH/DELETE | /api/entities/:type/:id | Read, update, or remove an entity. |
| POST | /api/entities/:type/:id/link | Link an entity to content or to another entity. |
| GET | /api/entities/:type/:id/related | Fetch related entities for display. |
| GET | /api/graph/:type/:id | Graph traversal endpoint for the explorer view. |

## UI Screens

- Entity Library (list/filter per entity type)

- Entity Detail page with a Related panel

- Entity Linker (used from within Issue Builder block editors)

- Knowledge Graph explorer view

## Components

- EntityCard

- EntityLinker (autocomplete with create-new)

- RelatedEntitiesPanel

- GraphExplorer

- TechnologyRadarBlockEditor

## State Management

Entity linking uses async-searchable select components backed by server queries; graph explorer state (selected node, traversal depth) is held in URL query parameters so views are shareable and bookmarkable.

## Supabase Changes

- RLS: public read access to published entity metadata; writes restricted to Researcher and Editor roles

- Indexes on junction tables to keep traversal queries performant as the graph grows

## AI Integrations

- None in this milestone.

## Acceptance Criteria

- Entities can be created and linked to articles and to each other

- An entity detail page correctly displays related entities across at least two hops

- The Technology Radar block renders from linked technology entities, not free text

## Testing Strategy

- Unit tests on junction/link CRUD operations

- Integration tests validating traversal query correctness and reviewing query plans for indexed joins

- UI test on entity-linker autocomplete behavior

## Risks and Dependencies

- Depends on Milestone 4 (blocks reference entities) and Milestone 6 (wisdom entries participate in the graph)

- Choosing typed junction tables over a generic polymorphic link table is a deliberate, documented decision (design document Section 6.1) — revisiting it mid-build would be costly, so it should not be relitigated during implementation

# Milestone 8: Search

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2–3 weeks | Milestones 5, 7 |

## Objective

Deliver global full-text and semantic search across all content and reference entity types, respecting publication and role-based visibility.

## Scope

In Scope

- PostgreSQL full-text search indexes

- pgvector embedding generation and storage pipeline

- Unified search API spanning all content types

- Global and scoped search UI

Out of Scope

- Search-driven automatic wisdom recommendation (documented fast-follow, builds directly on this milestone)

## Features

- Global search bar / command palette

- Filtered search by content type, publication, and tag

- Semantic “more like this” suggestions

- Background embedding backfill for existing content

## User Stories

- As a Reader, I want to search across issues, wisdom entries, and companies from one search bar, so that I don't have to know which content type holds what I'm looking for.

- As an Editor, I want to find related prior coverage of a topic while drafting an issue, so that we avoid duplicating or contradicting earlier reporting.

- As a Subscriber, I want search results ranked by relevance, not just recency, so that the most useful result surfaces first.

## Database Changes

- Embedding (vector) columns added to searchable tables: articles, blocks, wisdom_entries, technologies, companies, and other entity tables

- Generated tsvector columns for full-text search

- IVFFlat/HNSW index on embedding columns; GIN index on tsvector columns

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| GET | /api/search | Full-text search with query, type, and publication filters. |
| GET | /api/search/semantic | Semantic (embedding-similarity) search. |
| POST | /api/admin/search/reindex | Admin: trigger a full reindex/backfill. |

## UI Screens

- Global search overlay / command palette

- Search results page with faceted filters

- “Related content” widget embedded in the reading experience and in the Issue Builder's AI context panel

## Components

- SearchCommandPalette

- SearchResultsList

- SearchFacets

- RelatedContentWidget

## State Management

Search query and filter state held in URL parameters; debounced client-side queries call the server search API; results are cached briefly client-side to avoid redundant calls when toggling facets.

## Supabase Changes

- A scheduled job (Supabase Edge Function or pg_cron) generates embeddings on content create/update via the provider's embedding endpoint

- Search queries are RLS-aware, filtering out unpublished or unauthorized content rather than relying on the UI alone to hide it

## AI Integrations

- Embedding generation calls to the OpenAI/Claude embedding endpoints, extending the Milestone 5 provider abstraction with an embedText operation.

## Acceptance Criteria

- Search returns relevant results across every listed content type within the performance target (design document Section 11)

- Semantic search meaningfully surfaces related content beyond exact keyword matches

- Search results respect RLS — no unpublished or unauthorized content ever appears

## Testing Strategy

- Relevance QA against a curated set of representative queries

- Integration tests confirming RLS-filtered results

- Performance testing of index query latency at representative data volume

## Risks and Dependencies

- Depends on Milestone 7 (entities to search over) and Milestone 5 (reused provider abstraction)

- Bulk embedding backfill has real cost and latency implications — mitigated with batched, rate-limited background processing

- Keeping tsvector/embedding columns in sync on every content edit adds write-path complexity, addressed via triggers or a queue-based reindexing approach rather than synchronous inline computation

# Milestone 9: Analytics

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2 weeks | Milestones 3, 4, 5, 6, 7 |

## Objective

Provide editorial and operational analytics dashboards covering publication growth, engagement, content performance, and AI cost.

## Scope

In Scope

- Event capture pipeline

- Aggregation tables / materialized views

- Dashboard UI covering growth, engagement, content performance, and AI cost

Out of Scope

- Predictive/forecasting analytics (not part of the initial platform per design document Section 3.2)

## Features

- Publication and subscriber growth charts

- Engagement metrics: reading time, open rate, click rate

- Most-read content, top technologies/companies, trending skills

- Wisdom engagement metrics

- AI cost dashboard (rollup of Milestone 5's ai_jobs data)

## User Stories

- As an Editor-in-Chief, I want to see subscriber growth and engagement trends, so that I can evaluate how a publication is performing over time.

- As an Editor, I want to see which articles or blocks performed best, so that future coverage decisions are informed by what readers actually engage with.

- As a Super Admin, I want an AI cost dashboard, so that I can monitor AI spend against budget.

## Database Changes

- analytics_events (event_type, entity_type, entity_id, user_id nullable, publication_id, metadata JSONB, occurred_at)

- Materialized views / rollup tables: daily_publication_metrics, content_engagement_summary

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| POST | /api/events | Client-side event capture (reads, clicks, opens). |
| GET | /api/publications/:id/analytics/overview | Growth and engagement overview. |
| GET | /api/publications/:id/analytics/content | Content performance breakdown. |
| GET | /api/publications/:id/analytics/ai-cost | AI cost and usage rollup. |
| GET | /api/analytics/export | Export a report. |

## UI Screens

- Analytics Dashboard (overview)

- Content Performance view

- AI Cost & Usage view

- Export / report screen

## Components

- MetricCard

- TimeSeriesChart

- TopContentTable

- DateRangePicker

- ExportButton

## State Management

Dashboard filters (date range, publication) held in URL parameters; chart data is served from materialized views refreshed on a schedule rather than computed live per request, keeping dashboard loads fast.

## Supabase Changes

- Scheduled job (pg_cron or Edge Function) refreshing materialized views

- RLS on analytics_events: writes via a server-side service role, reads scoped by publication and role

- A defined retention policy for raw event data, consistent with the data-privacy commitments in design document Section 7.4

## AI Integrations

- None new; this milestone consumes ai_jobs data produced in Milestone 5.

## Acceptance Criteria

- Dashboards display accurate metrics against seeded/staging data

- Materialized views refresh on schedule without manual intervention

- Analytics access is correctly scoped by publication and role

## Testing Strategy

- Unit tests on aggregation logic

- Integration tests comparing rollup output against raw event data on a known fixture set

- UI snapshot tests on charts

## Risks and Dependencies

- Depends on Milestone 3 (publication scoping) and on content-producing Milestones 4, 6, and 7 to have something to measure, plus Milestone 5 for AI cost data

- Event volume at scale could strain a single events table — plan for partitioning or archival ahead of the Milestone 11 performance pass rather than after

- Event capture must stay within the data-privacy commitments in the design document; review retention rules before launch, not after

# Milestone 10: Publishing Pipeline

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| L | 3 weeks | Milestones 3, 4, 9 |

## Objective

Deliver the actual distribution of published issues to subscribers via email and the public web, plus PDF export and scheduled-publish automation.

## Scope

In Scope

- Email rendering and transactional sending

- PDF export from issue block content

- Public issue and publication web pages

- Subscribe / unsubscribe flow

- Scheduled-publish job execution

Out of Scope

- Paid subscription billing (not part of the initial platform per design document Section 3.2)

## Features

- Email template rendering from issue blocks

- Transactional send via an email service provider

- PDF export from issue blocks

- Public, SEO-friendly reading pages

- Subscribe / unsubscribe flow

- Scheduled-publish execution at the configured time

## User Stories

- As a Subscriber, I want to receive a well-formatted email when a new issue publishes, so that I can read it in the way I already check content.

- As a Reader, I want to read an issue on the web with a clean, accessible layout, so that the reading experience matches the editorial quality of the writing.

- As an Editor, I want to schedule an issue to auto-publish at a specific time, so that issues go out reliably on our cadence without someone manually clicking publish.

- As a Subscriber, I want a one-click unsubscribe, so that I can leave a mailing list without friction, as required by good practice.

## Database Changes

- subscriptions (subscriber_id, publication_id, status, subscribed_at, unsubscribed_at)

- delivery_logs (issue_id, subscriber_id, channel, status, sent_at, opened_at, clicked_at)

- scheduled_jobs (issue_id, run_at, status), following the same job-tracking pattern established by ai_jobs in Milestone 5

## API Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| POST | /api/publications/:id/subscribe | Subscribe to a publication. |
| POST | /api/subscriptions/:id/unsubscribe | Unsubscribe. |
| POST | /api/issues/:id/send | Send a published issue to subscribers. |
| GET | /api/issues/:id/export/pdf | Export an issue as PDF. |
| GET | /api/publications/:slug/issues/:issueSlug | Public read of a published issue. |
| POST | /api/webhooks/esp | Inbound webhook for delivery events (opens/clicks) from the email service provider. |

## UI Screens

- Public issue / article reading page

- Public publication landing page

- Subscribe form / landing page

- Unsubscribe confirmation

- Delivery Log / Send Status screen (editorial)

## Components

- EmailPreviewFrame

- PDFPreviewFrame

- PublicIssueLayout

- SubscribeForm

- DeliveryStatusTable

## State Management

Public reading pages are primarily server-rendered (SSR/ISR) with minimal client state. Send/schedule status is tracked server-side and streamed to the editorial Delivery Log screen via Supabase Realtime.

## Supabase Changes

- RLS allowing public (anonymous) read access to published-only issues and articles

- Realtime on delivery_logs for live send-status in the editorial UI

- Scheduled publish executed via pg_cron or an external scheduler invoking a publish Edge Function / API route

## AI Integrations

- None new.

## Acceptance Criteria

- A scheduled issue auto-publishes and sends at the configured time without manual action

- Email renders correctly across the tested set of major email clients

- PDF export matches the web layout at acceptable visual fidelity

- Unsubscribe is one click and immediately effective

- Public pages meet the accessibility and Core Web Vitals targets in design document Section 11

## Testing Strategy

- A defined checklist of email-client rendering tests

- Integration tests on scheduled-publish job execution

- End-to-end test of subscribe → receive → click in a staging environment

- Accessibility audit on public pages

## Risks and Dependencies

- Depends on Milestone 4 (issue content), Milestone 3 (publication templates), and overlaps with Milestone 9 on delivery analytics

- Email rendering across clients is historically fragile — budget explicit QA time rather than assuming a single test pass is sufficient

- Email deliverability (spam filtering) is an operational risk requiring domain authentication (SPF/DKIM/DMARC) setup, which should be tracked as an explicit infrastructure task

# Milestone 11: Performance Optimization

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2 weeks | Milestones 1–10 |

## Objective

Validate and tune the platform against the non-functional requirements in design document Section 11 before production hardening begins.

## Scope

In Scope

- Caching strategy for public and editorial pages

- Database index and query-plan review against real usage patterns

- Load testing against target subscriber concurrency

- Core Web Vitals pass

- Connection pooling review

Out of Scope

- New user-facing features (this milestone is tuning and validation, not feature work)

## Features

- CDN/edge caching configuration for public pages

- Index review and tuning against actual query patterns

- Read-replica evaluation if warranted by load-test results

- Image optimization pipeline

- Bundle-size audit

- Load test against target subscriber volume

## User Stories

- As a Reader, I want pages to load quickly even during a traffic spike after a new issue send, so that the reading experience doesn't degrade at the moment it matters most.

- As an Engineering Lead, I want to know the system's breaking point before production traffic finds it, so that we can plan capacity proactively instead of reactively.

- As an Editor, I want the AI Workspace to stay responsive during a generation-heavy day, so that deadline-driven work isn't blocked by system slowness.

## Database Changes

- Additional indexes identified from query analysis

- Possible partitioning of high-volume tables (analytics_events, ai_jobs, delivery_logs) if volume warrants it

- Connection pooling configuration (PgBouncer / Supabase pooler)

## API Endpoints

None new; existing endpoints instrumented with performance logging and tracing.

## UI Screens

- None new; existing screens optimized for lazy loading, image optimization, and code-splitting.

## Components

- Existing components audited and refactored for render performance: memoization and virtualization for long lists such as the Analytics tables and Entity Library.

## State Management

Review for unnecessary re-renders and redundant fetches; introduce a stale-while-revalidate caching layer where it demonstrably reduces load.

## Supabase Changes

- Connection pooling configuration finalized

- Query performance review (EXPLAIN ANALYZE) on hot paths identified during load testing

- Materialized view refresh cadence tuned based on observed load

## AI Integrations

- Review AI Workspace generation latency against the Section 11 SLA; consider streaming responses or a background-job UX pattern if generation time exceeds the target under load.

## Acceptance Criteria

- Load testing meets the target subscriber concurrency without error-rate degradation beyond an agreed threshold

- Public pages meet Core Web Vitals “Good” thresholds

- AI Workspace generation meets its defined SLA under representative load

- No N+1 query patterns remain on identified hot paths

## Testing Strategy

- Load/performance testing (e.g., k6) against a staging environment

- Lighthouse / Web Vitals checks integrated into CI

- Database query-plan review on hot paths

- AI generation latency benchmarking under load

## Risks and Dependencies

- Depends on all prior functional milestones being feature-complete, since tuning requires representative content and traffic patterns

- Performance issues discovered here may require schema or architecture changes that ripple back into earlier milestones — budget contingency time rather than treating this as a fixed-scope pass

# Milestone 12: Production Deployment

| Complexity | Duration | Dependencies |
| --- | --- | --- |
| M | 2 weeks, plus remediation buffer | Milestones 1–11 |

## Objective

Harden, security-review, and launch the platform, closing out with a rehearsed rollback procedure and a go/no-go checklist.

## Scope

In Scope

- Full RLS policy audit across every table

- Dependency and vulnerability scanning

- Secrets rotation review

- Production monitoring and alerting setup

- Launch runbook and go/no-go checklist

- Rollback procedure, rehearsed in staging

Out of Scope

- Any new functionality — this milestone is exclusively hardening, validation, and launch readiness

## Features

- RLS policy audit and remediation

- Vulnerability/dependency scan and remediation

- Production monitoring and alerting integration

- Launch runbook and go/no-go checklist

- Disaster-recovery / backup restore drill

## User Stories

- As a Security reviewer, I want to confirm no RLS policy allows cross-tenant data access before launch, so that we can launch with confidence in the platform's core isolation guarantee.

- As an Engineering Lead, I want an on-call runbook, so that incidents are handled predictably rather than improvised under pressure.

- As an Executive stakeholder, I want a go/no-go checklist, so that launch readiness is assessed objectively rather than by gut feel.

## Database Changes

- Final migration review and consolidation

- RLS policy audit fixes as needed

- Backup and point-in-time-recovery configuration confirmed

## API Endpoints

None new; rate-limiting and abuse-protection settings reviewed across all existing endpoints.

## UI Screens

- None new; a final cross-browser/cross-device QA pass across all existing screens.

## Components

- None new; a final accessibility and visual QA pass across all existing components.

## State Management

None new.

## Supabase Changes

- Production project finalized: backups, point-in-time recovery, and connection limits confirmed

- End-to-end audit logging confirmed

- Monitoring/alerting integrated (error tracking, uptime checks)

## AI Integrations

- Production AI provider API key rotation and budget alerting on spend.

## Acceptance Criteria

- An RLS penetration test finds no cross-tenant data exposure

- Monitoring and alerting are live and verified via a simulated incident that triggers the expected alert

- The go/no-go checklist is fully green

- The rollback procedure has been rehearsed at least once in staging

## Testing Strategy

- A third-party or internal security review / penetration test

- A full regression end-to-end suite run against a production-like environment

- A disaster-recovery drill (restore from backup)

## Risks and Dependencies

- Depends on all prior milestones being complete and stable

- Security findings discovered this late could delay launch — mitigated by the incremental RLS testing already built into Milestones 2 and 4, so this milestone should surface confirmations rather than first-time discoveries